## Clorox_8.1p2_Upgrade_Steps
Task Name | Due Date | Done | Assigned To | Status | Comments
Upgrade Steps
Stop all instances of Tomcat that are hosting IdentityIQ in the environment being targeted for patch.
Login to the application server using sudo access and stop tomcat
Repeat on all instances of Tomcat where IdentityIQ is being patched
Take a full backup of the identityiq and identityiqPlugin schema/database
Upgrade IQService
Login as Administrator and take backup of existing IQService installation.
Run the command prompt or PowerShell as Administrator
Ensure that IQService is stopped through Applet Services or by using the following command:
IQService.exe -k
Uninstall IQService using the following command:
IQService,exe -u
Extract the latest IQService in the existing installation directory iiq-8.1p2\WEB-INF\bin\win\IQService.zip
Install IQService using the following command:
IQService -i |  |  |  |  | Instance 1 (uses default port)
IQService -i -p 5052 |  |  |  |  | Instance 2
Start IQService from services or by using the following command:
IQService.exe -s
Make sure the service account for IQService is properly configured
IQService.exe -a CLOROX\SvcIIQL
Restart the IQService
Make sure the IQService is running as expected
Take a backup of the current IdentityIQ application under the $TOMCAT_HOME/webapps/identityiq directory.
Copy the latest war file with the timestamp in the webapps location
Extract the war file for the new version and overlay onto the existing application directory.
Update the iiq.properties file as required.
Execute the database upgrade scripts to upgrade the database.
Re-apply any changes needed to the application (e.g.: branding changes, etc.)
Execute the steps/lines 22 through 27 to all instances of the application server in the environment.
Once we upgrade the IdentityIQ application in one server instance, need to copy the Identityiq folder in all the instances
Start Tomcat in all instances of Tomcat that are hosting IdentityIQ
Navigate to the home page and validate the install.
Launch a browser window and navigate to the direct URL for IdentityIQ on this server
Verify that the login page is seen, and login with IIQ login credentials
Navigate to the Debug -> About page and verify that the install version shown is as expected
Open Active Directory application and make sure the test connection is successful with the upgraded IQService credentails